## Project Charter
Project Charter
Project Title | Oliver's App Project
Business Case | Design, Develop and Deploy a smartphone app designed for fun and wholesome conversation.
High-Level Work/Definition | (1) The official app will be user-friendly and as bug free as is feasable. (2) Milestone will be reached upon our 1,000th active user (3) An ongoing goal of having a rating score of 4.8 or higher out of 5.0 is reached.
Stakeholder Register | Founder - Oliver Warlick Investor - Grubby Bags Business Developer – Gandalf Frodo App Engineer – Oswald Snarf Quality Assurance Manager – HawkEye Gilligan Internal Tester – Bob Builder External Testers Customer
High-Level Risks | (1) Not completing the tasks in time for the official soft launch and not meeting the release date. (2)The risk of miscalculating the amount of resources it will take to complete the app with regard to manpower and computing resources. (3) Risk of a competitor stealing our ideas if we decide to go open source.
Budget | TBD
Dates | The 1st team kickoff project meeting is scheduled for 7/11/25
Notes | We may later decide to develop a version of the app for household computers.
WBS is on the second tab

## Olivers App WBS
Oliver's App Work Breakdown Structure (WBS)
PROJECT TITLE: Oliver's App
PROJECT TEAM NAMES: |  | Oliver Warlick, Gandalf Frodo, Oswald Snarf, HawkEye Gilligan, Bob Builder, External testers
WBS CODE | TASK TITLE | TASK OWNER | START DATE | DUE DATE |  |  | LINK/RESOURCE/NOTES
[5 empty] | DIFFICULTY | STATUS
[5 empty] | 1 = SIMPLE; 3 = COMPLEX | (BLANK CELLS = NOT STARTED)
1.1 | Company Inception Phase
1.1.1 | Develop a concept for the app | Oliver | 2025-06-25 | 2025-06-25 | 1 | Started
1.1.1.2 | Create a mission statement | Oliver | 2025-07-25 | 2025-07-25 | 1 | Started
1.1.1.3 | Create a company values statement | Oliver | 2025-07-25 | 2025-08-25 | 1 | Started
1.1.1.4 | Define our niche | Oliver | 2025-07-25 | 2025-08-25 | 1 | Started
1.1.2 | Create a list of resources needed and cost document | Gandalf | 2025-07-25 | 2025-08-25 | 2 | Started
1.1.3 | Develop a short, medium, and long term business plan | Gandalf | 2025-07-25 | 2025-08-25 | 2 | Started
Oliver ultimately gets the final say on the company core values, mission statement, and general direction of the app being develop. During this phase Oliver will be working closely with Gandalf to ensure the company ethos and the business strategy remain viable. Oswald, the app engineer will also be present during this time to help shapre the direction of the app as will HawkEye to ensure the quality of the app remains top-notch.
1.2 | Product Design Phase
1.2.1 | Design a MVP (minimum viable product) for the app | Oswald | 2025-07-25 | 2025-10-25 | 3 | Started | This will be one of the most challenging phases of the project; The actuall development of the application. Oliver will also be supporting the application development but Oswald is the accountable party and the one responsible. During this phase we run the risk of not having enough employees to develop the app on time and so we are prepared to hire another engineer if need be. Business develper Gandlaf will be consulted during thise phase to ensure our business goals stay focal as will HawkEye.
1.3 | Minimum Viable Product Phase
1.2.2 | Arrange to have MVP tested internally | HawkEye | 2025-10-25 | 2025-10-25 | 1
1.2.2.1 | Test the MVP for useability, bugs, etc | Bob Builder | 2025-10-25 | 2025-02-25 | 2
1.2.3 | Fig bugs and use feedback to enhance app | Oswald | 2025-10-25 | 2025-02-25 | 3
1.2.4 | Work with team to determine when app is ready for beta testing | Oliver | 2025-12-25 | 2025-02-26 | 2
1.4 | Beta-Testing Phase
1.4.1 | Arrange to have the app Beta-tested | HawkEye | 2025-02-26 | 2025-02-26 | 1
1.4.1.1 | Test the app and provide feedback | Bob Builder | 2025-02-26 | 2025-04-26 | 2 |  | Bob Builder is our internal tester; HawkEye will also be doing some testing as will our vetted beta-testers
1.4.2 | Fig bugs and use feedback to enhance app | Oswald | 2025-02-26 | 2025-04-26 | 3
1.4.3 | Work with operations team to determine when app is ready for soft-launch | Oliver | 2025-03-26 | 2025-04-26 | 2
1.5 | Soft-Launch Phase
1.5.1 | Soft-Launch the app and label it "early release" | HawkEye | 2025-04-26 | 2025-04-26 | 1
1.5.1.1 | Test the app and provide feedback | Bob | 2025-04-26 | 2025-08-26 | 2 |  | Bob Builder is our internal tester; HawkEye will also be doing some testing as will our vetted beta-testers and the folks who are using the early-access verison of our app
1.5.2 | Fig bugs and use feedback to enhance app | Oswald | 2025-04-26 | 2025-08-26 | 3
1.5.3 | Work with operations team to determine when app is ready for official release | Oliver | 2025-05-26 | 2025-08-26 | 2
1.6 | Official Release Phase
1.6.1 | Officially release the app to the public | Oliver | 2025-08-26 | 2025-08-26 | 1
2.1 | Maintenance Phase
2.1.1 | Monitor the app ensuring it is functioning properly | HawkEye | 2025-08-26 | Ongoing | 2
2.1.2 | Respond to user feedback as needed | Oswald | 2025-08-26 | Ongoing | 2 |  | Bob and HawkEye will continue to do testing and we will monitor feedback from our customers. We will also have feedback meetings with our operations team to make sure we are not missing any feedback from the customers.
2.1.3 | Work with operations team to ensure the app stay prominent | Oliver | 2025-08-26 | Ongoing | 2
3.1 | Hawaii Company Retreat Milestone Celebration
3.1.1 | Participate in the company retreat in Hawaii following our 1,000th active user and a 4.8 star rating (out of 5 stars) | Oliver | TBD | TBD (1 week) | 2

## Gantt Chart
Task ID | Task Title | Task Owner | Start Date | Due Date | Duration (Days) | Dependencies | Milestone
1.1.1 | Develop a concept for the app | Oliver | 2025-06-25 | 2025-06-25 | 1
1.1.1.2 | Create a mission statement | Oliver | 2025-07-02 | 2025-07-02 | 1 | 1.1.1
1.1.1.3 | Create a company values statement | Oliver | 2025-07-02 | 2025-08-02 | 32 | 1.1.1
1.1.1.4 | Define our niche | Oliver | 2025-07-02 | 2025-08-02 | 32 | 1.1.1
1.1.2 | Create a list of resources needed and cost document | Gandalf | 2025-07-02 | 2025-08-02 | 32 | 1.1.1
1.1.3 | Develop a short, medium, and long term business plan | Gandalf | 2025-07-02 | 2025-08-02 | 32 | 1.1.1
1.2 | Product Design Phase |  | 2025-07-02 | 2025-10-02 | 93 | 1.1 | Phase Start
1.2.1 | Design a MVP (minimum viable product) for the app | Oswald | 2025-07-02 | 2025-10-02 | 93 | 1.1
1.3 | Minimum Viable Product Phase |  | 2025-10-02 | 2026-02-26 | 147 | 1.2.1 | Phase Start
1.2.2 | Arrange to have MVP tested internally | HawkEye | 2025-10-02 | 2025-10-02 | 1 | 1.2.1
1.2.2.1 | Test the MVP for usability, bugs, etc | Bob Builder | 2025-10-02 | 2026-02-26 | 147 | 1.2.2
1.2.3 | Fix bugs and use feedback to enhance app | Oswald | 2025-10-02 | 2026-02-26 | 147 | 1.2.2.1
1.2.4 | Work with team to determine when app is ready for beta testing | Oliver | 2025-12-25 | 2026-02-26 | 63 | 1.2.3
1.4 | Beta-Testing Phase |  | 2026-02-26 | 2026-04-26 | 60 | 1.2.4 | Phase Start
1.4.1 | Arrange to have the app Beta-tested | HawkEye | 2026-02-26 | 2026-02-26 | 1 | 1.2.4
1.4.1.1 | Test the app and provide feedback | Bob Builder | 2026-02-26 | 2026-04-26 | 60 | 1.4.1
1.4.2 | Fix bugs and use feedback to enhance app | Oswald | 2026-02-26 | 2026-04-26 | 60 | 1.4.1.1
1.4.3 | Work with operations team to determine when app is ready for soft-launch | Oliver | 2026-03-26 | 2026-04-26 | 31 | 1.4.2
1.5 | Soft-Launch Phase |  | 2026-04-26 | 2026-08-26 | 122 | 1.4.3 | Phase Start
1.5.1 | Soft-Launch the app and label it "early release" | HawkEye | 2026-04-26 | 2026-04-26 | 1 | 1.4.3
1.5.1.1 | Test the app and provide feedback | Bob Builder | 2026-04-26 | 2026-08-26 | 122 | 1.5.1
1.5.2 | Fix bugs and use feedback to enhance app | Oswald | 2026-04-26 | 2026-08-26 | 122 | 1.5.1.1
1.5.3 | Work with operations team to determine when app is ready for official release | Oliver | 2026-05-26 | 2026-08-26 | 92 | 1.5.2
1.6 | Official Release Phase |  | 2026-08-26 | 2026-08-26 | 1 | 1.5.3 | Phase Start
1.6.1 | Officially release the app to the public | Oliver | 2026-08-26 | 2026-08-26 | 1 | 1.5.3 | Official Release
2.1 | Maintenance Phase |  | 2026-08-26 | Ongoing | - | 1.6.1 | Phase Start
2.1.1 | Monitor the app ensuring it is functioning properly | HawkEye | 2026-08-26 | Ongoing | - | 1.6.1
2.1.2 | Respond to user feedback as needed | Oswald | 2026-08-26 | Ongoing | - | 2.1.1
2.1.3 | Work with operations team to ensure the app stays prominent | Oliver | 2026-08-26 | Ongoing | - | 2.1.2
3.1 | Hawaii Company Retreat Milestone Celebration |  | TBD | TBD | 7 | 1.6.1, 1000 Users, 4.8 Rating | Milestone
3.1.1 | Participate in the company retreat in Hawaii... | Oliver | TBD | TBD | 7 | 3.1
Oliver ultimately gets the final say on the company core values, mission statement, and general direction of the app being develop. During this phase Oliver will be working closely with Gandalf to ensure the company ethos and the business strategy remain viable. Oswald, the app engineer will also be present during this time to help shapre the direction of the app as will HawkEye to ensure the quality of the app remains top-notch. The actuall development of the application will most likely be the most challenging phase of the project. Oliver will also be supporting the application development but Oswald is the accountable party and the one responsible. During this phase we run the risk of not having enough employees to develop the app on time and so we are prepared to hire another engineer if need be. Business develper Gandlaf will be consulted during thise phase to ensure our business goals stay focal as will HawkEye.

## Kanban Board
To Do | In Progress | Testing | Blocked | Done
1.1.1 Develop a concept for the app (Oliver) | 1.1.1 Develop a concept for the app (Oliver) | 1.2.2 Arrange to have MVP tested internally (HawkEye)
1.1.1.2 Create a mission statement (Oliver) | 1.1.1.2 Create a mission statement (Oliver) | 1.2.2.1 Test the MVP for usability, bugs, etc (Bob Builder)
1.1.1.3 Create a company values statement (Oliver) | 1.1.1.3 Create a company values statement (Oliver) | 1.4.1 Arrange to have the app Beta-tested (HawkEye)
1.1.1.4 Define our niche (Oliver) | 1.1.1.4 Define our niche (Oliver) | 1.4.1.1 Test the app and provide feedback (Bob Builder)
1.1.2 Create a list of resources needed and cost document (Gandalf) | 1.1.2 Create a list of resources needed and cost document (Gandalf) | 1.5.1.1 Test the app and provide feedback (Bob Builder)
1.1.3 Develop a short, medium, and long term business plan (Gandalf) | 1.1.3 Develop a short, medium, and long term business plan (Gandalf)
1.2.1 Design a MVP (minimum viable product) for the app (Oswald) | 1.2.1 Design a MVP (minimum viable product) for the app (Oswald)
1.2.2 Arrange to have MVP tested internally (HawkEye)
1.2.2.1 Test the MVP for usability, bugs, etc (Bob Builder)
1.2.3 Fix bugs and use feedback to enhance app (Oswald)
1.2.4 Work with team to determine when app is ready for beta testing (Oliver)
1.4.1 Arrange to have the app Beta-tested (HawkEye)
1.4.1.1 Test the app and provide feedback (Bob Builder)
1.4.2 Fix bugs and use feedback to enhance app (Oswald)
1.4.3 Work with operations team to determine when app is ready for soft-launch (Oliver)
1.5.1 Soft-Launch the app and label it "early release" (HawkEye)
1.5.1.1 Test the app and provide feedback (Bob Builder)
1.5.2 Fix bugs and use feedback to enhance app (Oswald)
1.5.3 Work with operations team to determine when app is ready for official release (Oliver)
1.6.1 Officially release the app to the public (Oliver)
2.1.1 Monitor the app ensuring it is functioning properly (HawkEye)
2.1.2 Respond to user feedback as needed (Oswald)
2.1.3 Work with operations team to ensure the app stays prominent (Oliver)
3.1.1 Participate in the company retreat in Hawaii following our 1,000th active user and a 4.8 star rating (out of 5 stars) (Oliver)
This project requires a lot of colloboration between teams and so having a datasheet that is easy to visualize and easy to use is essential to good workflow. The Kanban board does a great job of breaking down each task into bite sized bits. I added a testing column because those fields should help keep the operations team (app developers, business developers, founder) up to speed. Currently nothing is blocked but in the event blockers arise there is already a column to address those. The Kanban board makes is less challenging to gague the progression of the project; For example, If there are a lot of cards piling up in 1 column; it probably means it's at risk of being a bottle neck. I did add all the tasks for each phase into the Kanban board as opposed to create a new column for tasks on standby and so it may feel more daunting than it actually is.